## Log
| RAID Log | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[9 empty] | Risk | 11 | 1 | 6 | 4 | 0 | 0
| Project title: | SYB Journey Planner | Project number: | 3 | Project leader: | Project Manager |  |  | Assumption | 2 | 0 | 0 | 1 | 1 | 0
[9 empty] | Issue | 0 | 0 | 0 | 0 | 0 | 0
|  | You need only to fill the white cells. | Revision date: | 2025-12-10 | Revision number: | 1.3 |  |  | Dependency | 2 | 0 | 2 | 0 | 0 | 0
| Select … |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 15 |  |  |  |  | 15
| RAID Category | Description | Impact | Owner | Priority | RPN (for risks) | Status
1 | Assumption | Vague information regarding requirements | Low | Business analyst | Moderate | 10 | Open | Risk
2 | Risk | Scope Creep | High | Project manager | High | 2 | Open | Assumption
3 | Risk | Resistance to change | Medium | Project manager | Moderate | 11 | Open | Issue
4 | Risk | Legal and compliance issues | High | Business analyst | High | 3 | Open | Dependency
5 | Risk | Schedule delays | Medium | Project manager | High | 4 | Open
6 | Risk | Hardware technology failures | Medium | QA specialist | Moderate | 12 | Open | Open
7 | Risk | Software technology failures | High | QA specialist | Critical | 1 | Open | Closed
8 | Risk | Communication issues | High | Project manager | High | 5 | Open
9 | Risk | Resource management | High | Project sponsor | High | 6 | Open | Critical
10 | Risk | Staff sickness | High | Project manager | Moderate | 13 | Open | High
11 | Assumption | Acts of nature | Low | QA specialist | Low | 15 | Open | Moderate
12 | Dependency | Mapping Provider API | High | Project manager | High | 7 | Open | Low
13 | Dependency | Branding assets (e.g. UI, logos, colour) | Medium | Business analyst | High | 8 | Open | Negligible
14 | Risk | Fixed budget (£65,000) | Medium | Project sponsor | Moderate | 14 | Open
15 | Risk | Product does not meet client requirements | High | Business analyst | High | 9 | Open
16
17
18
19
20
21
22
23
24
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This template allows project managers to track risks, assumptions, issues and dependencies.
It should drive to take the necessary actions in order to ensure successful implementation of the project.
Use this log at the beginning of the project, then regularly review and update it as necessary through regular project meetings.

## Dashboard
RAID Dashboard
| Project title: | SYB Journey Planner |  |  | Project number: | 3 | Revision date: | 2025-12-10
| Risks |  | Assumptions |  | Issues |  | Dependencies
| 1 | Critical | 0 | Critical | 0 | Critical | 0 | Critical | 1
| 6 | High | 0 | High | 0 | High | 2 | High | 8
| 4 | Moderate | 1 | Moderate | 0 | Moderate | 0 | Moderate | 5
| 0 | Low | 1 | Low | 0 | Low | 0 | Low | 1
| 0 | Negligible | 0 | Negligible | 0 | Negligible | 0 | Negligible | 0
| 11 |  | 2 |  | 0 |  | 2 |  | 15
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This dashboard allows project teams to review all relevant information related to a project at a glance.