## Function Point Analysis
Complexity of Functions
Factor | Simple | Average | Complex
External Inputs | 1 x 2 | 1 x 7 | 0 x 0
External Outputs | 0 x 0 | 1 x 6 | 0 x 0
External Inquiries | 1 x 1 | 2 x 7 | 0 x 0
Internal Logical Files | 1 x 1 | 2 x 6 | 0 x 0
External Interface Files | 1 x 3 | 0 x 0 | 2 x 10
Functional point computation
| Simple | Average | Complex
External Inputs | 2 | 7 | 0
External Outputs | 0 | 6 | 0
External Inquiries | 1 | 14 | 0
Internal Logical Files | 1 | 12 | 0
External Interface Files | 3 | 0 | 20
Unadjusted Function Points (UFP) |  |  | 66
Technical Complexity Factor (TCF) |  |  | 1.31
Adjusted function points |  |  | 86.46

## Factors
Current factors used in Sheet1
Type | What I think it means | Factors and category and weight
External Inputs | User inputs which update files | 1. Register account (Simple - 2) 2. Save favourite bus stop (Average - 7)
External Outputs | Output with processed pulled data | 1. Alerts about bus being delayed (Average - 6)
External Inquiries | Ready only requests only | 1. Search for/plan a journey (Average - 7) 2. Check the arrival time of buses on bus stops (Average - 7) 3. View the list of saved favourite bus stops (Simple - 1)
Internal Logical Files | Data that this system manages | 1. Users table (proper database) (Simple- 1) 2. Bus stop table (maybe proper database table and local version where user saves to favourites?) (Average - 6) 3. Search history table in local database? (Average - 6)
External Interface Files | Data that this system reads, not manages | 1. Bus timetables database (Simple - 3) 2. Real-time bus tracking API (Complex - 10) 3. Payment API (Complex - 10)