## Sheet1
Risk Register
ID | Description | Probability | Impact | Category | Response | Comments
1 | Vague information regarding requirements | Low | Low | Very Low | Reduce | by seeking clarification of requirements
2 | Scope Creep | High | High | Very High | Reduce | by evaluating and approving/disapproving changes
3 | Resistance to change | Low | Medium | Quite Low | Reduce | by encouraging change/reassuring client
4 | Legal and compliance issues | Medium | High | Quite High | Avoid | legal repercussion
5 | Schedule delays | Low | Medium | Quite Low | Contingency | implement mitigation strategies
6 | Hardware technology failures | Low | High | Medium | Contingency | replace problematic devices/hardware
7 | Software technology failures | High | Medium | Quite High | Avoid | use proven technology
8 | Communication issues | High | High | Very High | Reduce | by maintaining open communication
9 | Resource management | Low | Medium | Quite Low | Reduce | by allocating resources efficiently
10 | Staff sickness | Medium | High | Quite High | Transfer | tasks or responsibilities to another staff member
11 | Acts of nature | Low | Low | Very Low | Accept | that there could be complications