## Sheet1
RACI Matrix
R | Responsible | people who does the work
A | Accountable | people who “owns” the work
C | Consultation | people who provide input before sign-off
I | Information | people who need to updated on progress and decisions
|  | Roles | Project Manager | Project Sponsor | Project Officer | Users | Business Analyst | Designer | Risk Manager | Software Team Leader | SoftwareEnginners | Quality Manager
|  | Packages/Tasks | Steering Group |  |  | User Group |  |  | Risk Management Group
|  | Planning | R | C | C |  | A | I | C | C | I | C
|  | Business Case | R | C | A | I | C | I | C | C | I | C
|  | Force Field Analysis | C | I | I |  | R |  |  | I | I
|  | COCOMO II | C | I | I |  | I | I | I | R | C | I
|  | Cost Management | R | C | R |  | A |  | C | C | I | I
|  | Risk Management | C | I | I |  | C |  | R | C | C | C
|  | Task Management | R | I | C |  | I | I | I | R | I | I
|  | RACI Matrix | A | I | R | I |  |  |  | C | I | C
|  | GANTT Chart | A | I | R |  | I | I | I | C | I | I
|  | Use Case Diagrams | I | I | I | I | R | I | I | C | I | C
|  | Quality Management | C | I | I | I | C | I |  | C | R | R
|  | wireframe | I | I | I | C | C | R |  | I | I | I
|  | Branding Integration | A | I | I |  | A | R |  | C |  | I
|  | High fidelity Prototype | I | I | I | C | C | R | I | C | I | I
|  | Video walkthrough | R | I | I |  | I | I | I | I | I | C
|  | Map API provider | C | I | I |  | I |  | I | A | R
|  | Cloud Hosting | C | I | I |  | I |  | I | A | R | C
|  | Database | I | I | I |  | C |  | I | A | R
|  | Final Deployed Software | A | I | I | C | C | I | C | R | R | C
|  | Source Code | I |  | I |  | I | I | I | A | R | C
|  | Test Report | C | I | I | C | C | I | I | I | R | A
|  | Deployment Document | A | I | I | I | I | I | C | R | R | C
|  | Compile runbooks | C | I | I |  | I |  | I | A | R | C
|  | Confirm access information | C | I | I |  |  | I |  | A | R
|  | Define support window | A | C | I |  | I |  |  | C | I
|  | final sign-off | R | A | I | I | I | I | I | I | I | C